PRISM-M Task Breakdown Structure (TBS)

MediSched AI

PRISM Phase: M – Milestone Execution
SmartX Technologies
Date: April 2026  |  Duration: 8 Weeks (4 Sprints)
Version: 1.0

# PRISM-M Task Breakdown Structure (TBS)

SmartX Technologies

PRISM Phase: M – Milestone Execution

Purpose: Convert the approved design into a predictable, testable execution plan. Tasks must be independently buildable, reviewable, and verifiable.

## 1. References

| Artifact | Document | Status |
| --- | --- | --- |
| PRISM-P | MediSched AI Problem Brief | Approved |
| PRISM-R | MediSched AI PRD-Lite (50 FRs, 17 NFRs, 12 Edge Cases) | Approved |
| PRISM-I | MediSched AI Solution Options Matrix (Django DRF + React selected) | Approved |
| PRISM-S | MediSched AI Design Document — 9 Django apps, 26 API endpoints, 8 data entities, 4-sprint rollout | Approved |

## 2. Execution Objectives

What functionality will exist at the end of each milestone?

| Milestone | Sprint | Weeks | Deliverable | Key Functionality |
| --- | --- | --- | --- | --- |
| M1 – Core Infrastructure | Sprint 1 | 1–2 | Project foundation + data management | Docker Compose running, all Django models migrated, JWT auth + RBAC enforced, Patient CRUD (API + UI), Doctor profile CRUD (API + UI), React SPA with login + routing |
| M2 – Scheduling Engine | Sprint 2 | 3–4 | PROTOTYPE DEMO | Doctor slot management (generate, block), Calendar view (FullCalendar + real-time WebSocket), Appointment booking (staff selects slot + patient), Django admin configured |
| M3 – AI Calling & Transcription | Sprint 3 | 5–6 | AI calling live | Celery worker running, Twilio outbound calls with 3-attempt escalation, Whisper transcription, Call log management (view, search, edit transcription) |
| M4 – Full System | Sprint 4 | 7–8 | FINAL DEMO | Automated SMS/email reminders (booking + 24hr), Analytics dashboard + CSV export, Edge case hardening, Security audit, Load testing, Full system demo |

Acceptance criteria alignment:

M1 validates: FR-UA-01–06, FR-PM-01–08, FR-DM-01–03

M2 validates: FR-DS-01–08, FR-CM-01–05 (including concurrent booking test)

M3 validates: FR-AC-01–08, FR-CD-01–06

M4 validates: FR-RM-01–04, FR-AN-01–04, all edge cases EC-01–12, all NFRs

## 3. Milestone Scope

Included (across all 4 sprints):

All 9 Django apps from PRISM-S: users, patients, doctors, scheduling, calling, transcriptions, reminders, analytics, realtime.

React SPA with 9 pages: Login, Calendar, PatientsList, PatientDetail, DoctorsList, DoctorSlots, CallLogs, TranscriptionDetail, AnalyticsDashboard.

All 26 API endpoints from PRISM-S Section 7.

Docker Compose (5 services), CI/CD via GitHub Actions, unit + integration + E2E tests.

Excluded (confirmed from PRISM-S non-goals):

Multi-center/multi-tenant, multi-language voice, patient self-registration, EHR/EMR integration, PDF export, recurring slot templates, HIPAA formal certification.

## 4. Epic Breakdown

| Epic ID | Epic Name | Sprint | PRISM-S Component | Key FRs Covered |
| --- | --- | --- | --- | --- |
| E-01 | Project Setup & Infrastructure | Sprint 1 (W1) | Section 4 (Architecture) | N/A (foundation) |
| E-02 | Auth & User Management | Sprint 1 (W1) | Section 5.1 (Users App) | FR-UA-01–06 |
| E-03 | Patient Management | Sprint 1 (W1–W2) | Section 5.2 (Patients App) | FR-PM-01–08 |
| E-04 | Doctor Management | Sprint 1 (W2) | Section 5.3 (Doctors App – profiles) | FR-DM-01–03 |
| E-05 | Doctor Slot Management | Sprint 2 (W3) | Section 5.3 (Doctors App – slots) | FR-DS-01–08 |
| E-06 | Calendar & Appointment Booking | Sprint 2 (W3–W4) | Sections 5.4, 5.9 (Scheduling, Realtime) | FR-CM-01–05 |
| E-07 | AI Outbound Calling | Sprint 3 (W5–W6) | Section 5.5 (Calling App) | FR-AC-01–08 |
| E-08 | Call Transcription | Sprint 3 (W6) | Section 5.6 (Transcriptions App) | FR-CD-01–06 |
| E-09 | Automated Reminders | Sprint 4 (W7) | Section 5.7 (Reminders App) | FR-RM-01–04 |
| E-10 | Analytics & Reporting | Sprint 4 (W7–W8) | Section 5.8 (Analytics App) | FR-AN-01–04 |
| E-11 | Hardening & Final Demo | Sprint 4 (W8) | Sections 9–12 (NFRs, Tests, Deployment) | All NFRs, EC-01–12 |

## 5. Story Breakdown

### Sprint 1 — Weeks 1–2: Core Infrastructure & Data Management

| Story ID | Epic | Story | Priority |
| --- | --- | --- | --- |
| S-01 | E-01 | Set up mono-repo, Docker Compose (5 services), Django project, React project (Vite) | Critical |
| S-02 | E-01 | Configure PostgreSQL, Redis, Django settings (DATABASES, CHANNEL_LAYERS, CELERY) | Critical |
| S-03 | E-02 | Implement custom User model with role field (Admin, Staff, Doctor, ReadOnly) | Critical |
| S-04 | E-02 | Implement JWT auth endpoints (login, refresh, logout) using Simple JWT | Critical |
| S-05 | E-02 | Implement DRF permission classes (IsAdmin, IsStaff, IsDoctor, IsReadOnly, IsAdminOrStaff) | Critical |
| S-06 | E-02 | Build React login page, auth context, Axios JWT interceptor | Critical |
| S-07 | E-03 | Implement Patient model, serializers, viewset with CRUD + search + duplicate phone detection | High |
| S-08 | E-03 | Build React Patients list page (search, table) and Patient detail page (form, appointment history) | High |
| S-09 | E-04 | Implement Doctor model, serializers, viewset with CRUD (Admin only) + self-edit (Doctor own profile) | High |
| S-10 | E-04 | Build React Doctors list page and Doctor profile edit form | High |
| S-11 | E-01 | Configure Django admin for all Sprint 1 models (User, Patient, Doctor) | Medium |
| S-12 | E-01 | Write unit tests for all Sprint 1 models, serializers, permissions, and viewsets | High |

### Sprint 2 — Weeks 3–4: Scheduling Engine (PROTOTYPE DEMO)

| Story ID | Epic | Story | Priority |
| --- | --- | --- | --- |
| S-13 | E-05 | Implement DoctorSlot model with status field (Available/Booked/Blocked), unique_together constraint | Critical |
| S-14 | E-05 | Implement slot auto-generation service (date, start, end, duration → bulk_create slots) | Critical |
| S-15 | E-05 | Implement overlap detection (reject if existing slots conflict) | Critical |
| S-16 | E-05 | Implement slot block/unblock endpoint (Doctor + Admin) | High |
| S-17 | E-05 | Build React "My Availability" page for doctors (date picker, time range, duration selector, release button) | High |
| S-18 | E-06 | Implement Appointment model and booking endpoint (POST /slots/{id}/book/) with select_for_update() | Critical |
| S-19 | E-06 | Implement WebSocket consumer (CalendarConsumer) + Django signal on DoctorSlot save/update | Critical |
| S-20 | E-06 | Build React Calendar page with FullCalendar (day/week/month views, color-coded slots) | Critical |
| S-21 | E-06 | Implement React WebSocket hook (useWebSocket) for real-time calendar updates | High |
| S-22 | E-06 | Build booking modal: search patient + select slot + confirm + see slot turn blue in real-time | High |
| S-23 | E-06 | Implement appointment cancellation endpoint (reverts slot to Available, sends SMS) | Medium |
| S-24 | E-06 | Write integration tests: concurrent booking (409), calendar data accuracy, WebSocket broadcast | Critical |
| S-25 | E-06 | Configure Django admin for DoctorSlot, Appointment models | Medium |
| S-26 | E-06 | PROTOTYPE DEMO preparation: seed test data (5 doctors, 50 patients, 3 days of slots) | High |

### Sprint 3 — Weeks 5–6: AI Calling & Transcription

| Story ID | Epic | Story | Priority |
| --- | --- | --- | --- |
| S-27 | E-07 | Configure Celery with Redis broker, 3 queues (calling, transcription, reminder), Celery Beat | Critical |
| S-28 | E-07 | Implement CallLog model with attempt tracking and outcome field | Critical |
| S-29 | E-07 | Implement call_patient Celery task: Twilio call initiation + 3-attempt escalation with ETA scheduling | Critical |
| S-30 | E-07 | Implement TwiML webhook endpoints: greeting (disclaimer + menu), handle-input, offer-slots, status-callback | Critical |
| S-31 | E-07 | Implement ManualCallbackTask model and creation on Attempt 3 failure | High |
| S-32 | E-07 | Implement POST /calling/initiate/ endpoint (triggers call_patient.delay()) | High |
| S-33 | E-07 | Build React Call Logs page (list calls by patient/date, show attempt number, outcome, transcription status) | High |
| S-34 | E-08 | Implement Transcription model linked to CallLog and Appointment | High |
| S-35 | E-08 | Implement transcribe_call Celery task: download recording from Twilio → send to Whisper API → store result | Critical |
| S-36 | E-08 | Implement transcription view/edit endpoints (Staff can edit text, track last_edited_by) | High |
| S-37 | E-08 | Build React Transcription detail page (view text, edit inline, save) | High |
| S-38 | E-07 | Write unit tests: Celery task idempotency, escalation logic, TwiML output. Integration tests: mock Twilio end-to-end call flow | Critical |

### Sprint 4 — Weeks 7–8: Reminders, Analytics, Hardening & Final Demo

| Story ID | Epic | Story | Priority |
| --- | --- | --- | --- |
| S-39 | E-09 | Implement ReminderLog model with channel and delivery_status tracking | High |
| S-40 | E-09 | Implement send_booking_reminder Celery task (SMS + email on booking) | High |
| S-41 | E-09 | Implement check_upcoming_reminders Celery Beat task (24hr window) + send_24h_reminder | High |
| S-42 | E-09 | Implement reminder retry logic (1 retry after 15 min on failure) | Medium |
| S-43 | E-10 | Implement analytics dashboard endpoint (utilization, call success, no-shows, per-doctor stats) | High |
| S-44 | E-10 | Implement CSV export endpoint (StreamingHttpResponse with filtered data) | High |
| S-45 | E-10 | Build React Analytics Dashboard page (charts, filters, export button) | High |
| S-46 | E-11 | Handle all edge cases EC-01–12: past-date slot rejection, invalid phone handling, deactivate doctor with bookings, etc. | High |
| S-47 | E-11 | Security hardening: audit logging middleware, TLS config, session expiry validation, RBAC matrix test | Critical |
| S-48 | E-11 | Load testing: 20 concurrent users, 500 slots calendar load, concurrent booking stress test | High |
| S-49 | E-11 | E2E tests: staff booking journey, doctor slot release, admin analytics export (Playwright) | High |
| S-50 | E-11 | FINAL DEMO preparation: full seed data, demo script, documentation | High |

## 6. Task Breakdown (Core Section)

Each story is broken into concrete, independently buildable tasks. Full task table for Sprint 1 and Sprint 2 shown below. Sprint 3–4 follow the same pattern.

### Sprint 1 Task Breakdown (Weeks 1–2)

| Task ID | Story | Description | Files / Components | Acceptance Criteria | Test | Depends On | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| T-001 | S-01 | Create mono-repo with /backend and /frontend directories | Root: docker-compose.yml, .env.example, README.md | Repo structure matches PRISM-S Section 4 layout | N/A | None | Eng Lead |
| T-002 | S-01 | Create docker-compose.yml with 5 services (react, django, celery, postgres, redis) | docker-compose.yml | docker-compose up starts all 5 services. Django accessible on :8000, React on :3000 | Integration | T-001 | Eng Lead |
| T-003 | S-01 | Initialize Django project with config/ directory (settings, urls, asgi, celery) | backend/config/ | Django runserver starts without errors. Celery connects to Redis. | Unit | T-002 | Backend Dev |
| T-004 | S-01 | Initialize React project with Vite + TypeScript + React Router | frontend/src/, vite.config.ts | npm run dev serves React SPA on :3000 with routing | N/A | T-002 | Frontend Dev |
| T-005 | S-02 | Configure Django settings: DATABASES (PostgreSQL), CHANNEL_LAYERS (Redis), CELERY_BROKER (Redis) | backend/config/settings.py | Django connects to PostgreSQL. Channels connects to Redis. | Unit | T-003 | Backend Dev |
| T-006 | S-03 | Create users app: Custom User model (email, role, is_active), register in INSTALLED_APPS, makemigrations | backend/users/models.py | User model with role choices (ADMIN, STAFF, DOCTOR, READONLY). Migration runs cleanly. | Unit | T-005 | Backend Dev |
| T-007 | S-04 | Implement JWT endpoints: POST /api/auth/login/, /refresh/, /logout/ using Simple JWT | backend/users/views.py, urls.py | Login returns access + refresh tokens. Refresh returns new access token. Protected endpoint returns 401 without token. | Integration | T-006 | Backend Dev |
| T-008 | S-05 | Implement DRF permission classes: IsAdmin, IsStaff, IsDoctor, IsReadOnly, IsAdminOrStaff | backend/users/permissions.py | Admin can access IsAdmin endpoint. Staff gets 403 on IsAdmin endpoint. Each role tested. | Unit | T-006 | Backend Dev |
| T-009 | S-06 | Build React Login page with email/password form, call POST /api/auth/login/ | frontend/src/pages/LoginPage.tsx | User can log in. JWT stored. Redirects to Calendar page. | E2E | T-004, T-007 | Frontend Dev |
| T-010 | S-06 | Implement AuthContext + Axios interceptor (attach JWT, handle 401 redirect) | frontend/src/contexts/AuthContext.tsx, services/api.ts | All API calls include Authorization header. 401 redirects to login. | Unit | T-009 | Frontend Dev |
| T-011 | S-07 | Create patients app: Patient model, DRF serializer, ModelViewSet with search filter | backend/patients/models.py, serializers.py, views.py | POST /patients/ creates patient. GET /patients/?search=name returns results. Duplicate phone returns 400. | Integration | T-008 | Backend Dev |
| T-012 | S-07 | Implement PatientDetailSerializer with nested appointment history | backend/patients/serializers.py | GET /patients/{id}/ returns patient details + appointment list | Unit | T-011 | Backend Dev |
| T-013 | S-08 | Build React Patients list page (search bar, table, pagination, "Add Patient" button) | frontend/src/pages/PatientsListPage.tsx | Search filters patients. Table shows name, phone, DOB. Click navigates to detail. | E2E | T-010, T-011 | Frontend Dev |
| T-014 | S-08 | Build React Patient detail page (edit form + appointment history tab) | frontend/src/pages/PatientDetailPage.tsx | Staff can edit patient fields. Appointment history displayed. | E2E | T-013 | Frontend Dev |
| T-015 | S-09 | Create doctors app: Doctor model, DRF serializer, ModelViewSet (Admin CRUD + Doctor self-edit) | backend/doctors/models.py, serializers.py, views.py | Admin creates doctor. Doctor can edit own name/phone/email but not specialization/status. | Integration | T-008 | Backend Dev |
| T-016 | S-10 | Build React Doctors list page and Doctor profile edit page | frontend/src/pages/DoctorsListPage.tsx, DoctorEditPage.tsx | Admin sees all doctors. Doctor sees only own profile. | E2E | T-010, T-015 | Frontend Dev |
| T-017 | S-11 | Configure Django admin: register User, Patient, Doctor models with search and list filters | backend/*/admin.py | Admin panel shows all models with search and filtering. | Manual | T-006, T-011, T-015 | Backend Dev |
| T-018 | S-12 | Write unit tests: User model, Patient model, Doctor model, all serializers, all permission classes | backend/*/tests/ | pytest passes. Coverage >80% on users, patients, doctors apps. | Unit | T-008, T-011, T-015 | Backend Dev |

### Sprint 2 Task Breakdown (Weeks 3–4)

| Task ID | Story | Description | Files / Components | Acceptance Criteria | Test | Depends On | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| T-019 | S-13 | Create DoctorSlot model with status, duration, booked_patient FK, unique_together(doctor, date, start_time) | backend/doctors/models.py | Migration runs. Duplicate (doctor, date, start_time) raises IntegrityError. | Unit | T-015 | Backend Dev |
| T-020 | S-14 | Implement generate_slots service function (bulk_create from date, start, end, duration) | backend/doctors/services.py | generate_slots(doctor, 2026-04-10, 09:00, 12:00, 30) creates 6 slots. | Unit | T-019 | Backend Dev |
| T-021 | S-15 | Implement overlap detection in generate_slots (query existing slots, reject conflicts) | backend/doctors/services.py | Attempting overlapping slots returns 400 with conflict details. | Unit | T-020 | Backend Dev |
| T-022 | S-16 | Implement slot block/unblock PATCH endpoint. Reject blocking booked slots. | backend/doctors/views.py | Block available slot: 200. Block booked slot: 400 error. | Integration | T-019 | Backend Dev |
| T-023 | S-17 | Build React "My Availability" page (date picker, start/end time, duration dropdown, generate button, slot list) | frontend/src/pages/DoctorSlotsPage.tsx | Doctor selects date + time + duration. Clicks generate. Slots appear in list. | E2E | T-020 | Frontend Dev |
| T-024 | S-18 | Implement Appointment model + POST /slots/{id}/book/ with select_for_update() | backend/scheduling/models.py, backend/doctors/views.py | Booking: slot status=Booked, Appointment created. Concurrent: first succeeds, second gets 409. | Integration | T-019 | Backend Dev |
| T-025 | S-19 | Implement CalendarConsumer WebSocket + DoctorSlot post_save signal for broadcast | backend/realtime/consumers.py, backend/doctors/signals.py | Slot change broadcasts to all connected WebSocket clients within 2 seconds. | Integration | T-005, T-019 | Backend Dev |
| T-026 | S-20 | Build React Calendar page with FullCalendar (dayGrid, timeGrid views, color-coded events) | frontend/src/pages/CalendarPage.tsx | Calendar displays slots. Available=green, Booked=blue, Blocked=grey. Filterable by doctor. | E2E | T-024 | Frontend Dev |
| T-027 | S-21 | Implement useWebSocket hook + integrate with Calendar page for live updates | frontend/src/hooks/useWebSocket.ts | When another user books a slot, calendar updates in real-time without page refresh. | Integration | T-025, T-026 | Frontend Dev |
| T-028 | S-22 | Build booking modal: patient search dropdown + confirm button + real-time slot color change | frontend/src/components/BookingModal.tsx | Staff clicks available slot → modal opens → searches patient → confirms → slot turns blue. | E2E | T-026, T-013 | Frontend Dev |
| T-029 | S-23 | Implement POST /appointments/{id}/cancel/ (revert slot, send cancellation SMS) | backend/scheduling/views.py | Cancelled appointment: slot reverts to Available, patient gets SMS. | Integration | T-024 | Backend Dev |
| T-030 | S-24 | Write concurrent booking integration test (2 simultaneous requests, 1 succeeds 1 gets 409) | backend/doctors/tests/ | Test passes with threading. One 200, one 409. No data corruption. | Integration | T-024 | Backend Dev |
| T-031 | S-25 | Configure Django admin for DoctorSlot, Appointment with list_display and filters | backend/doctors/admin.py, scheduling/admin.py | Admin panel shows slots/appointments with search and status filters. | Manual | T-019, T-024 | Backend Dev |
| T-032 | S-26 | Create seed data script: 5 doctors, 50 patients, 3 days of slots (mix of Available/Booked) | backend/config/management/commands/seed_demo.py | python manage.py seed_demo populates DB. Calendar shows realistic data. | Manual | T-024 | Backend Dev |

### Sprint 3 Task Breakdown (Weeks 5–6)

| Task ID | Story | Description | Files / Components | Acceptance Criteria | Test | Depends On | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| T-033 | S-27 | Configure Celery app in config/celery.py, register 3 queues, configure Celery Beat schedule | backend/config/celery.py, settings.py | Celery worker starts, connects to Redis, processes tasks from 3 queues. | Integration | T-005 | Backend Dev |
| T-034 | S-28 | Create CallLog model with attempt_number, outcome, twilio_call_sid, transcription_status | backend/calling/models.py | Migration runs. CallLog stores all required fields. | Unit | T-033 | Backend Dev |
| T-035 | S-29 | Implement call_patient Celery task: Twilio create call + 3-attempt escalation (ETA for 2hr retry) | backend/calling/tasks.py | Attempt 1 dispatched. On no-answer: Attempt 2 scheduled +2hr. On 3rd fail: ManualCallbackTask created. | Unit (mock Twilio) | T-034 | Backend Dev |
| T-036 | S-30 | Implement 4 TwiML webhook endpoints: greeting, handle-input, offer-slots, status-callback | backend/calling/views.py, urls.py | TwiML returns valid XML. Greeting plays disclaimer. handle-input processes DTMF. offer-slots reads live slots. | Integration | T-035 | Backend Dev |
| T-037 | S-31 | Implement ManualCallbackTask model + creation logic on 3rd attempt failure | backend/calling/models.py, tasks.py | After 3 failed attempts, ManualCallbackTask record exists with patient details. | Unit | T-035 | Backend Dev |
| T-038 | S-32 | Implement POST /calling/initiate/ endpoint (validates patient, dispatches call_patient.delay) | backend/calling/views.py | Staff calls endpoint → Celery task queued → CallLog created with attempt=1. | Integration | T-035 | Backend Dev |
| T-039 | S-33 | Build React Call Logs page (list with filters: patient, date, outcome; click to view transcription) | frontend/src/pages/CallLogsPage.tsx | Call logs displayed with attempt number, outcome, transcription status. Click navigates to transcription. | E2E | T-038 | Frontend Dev |
| T-040 | S-34 | Create Transcription model (call_log 1:1, text, status, last_edited_by) | backend/transcriptions/models.py | Migration runs. Transcription links to CallLog. | Unit | T-034 | Backend Dev |
| T-041 | S-35 | Implement transcribe_call Celery task: download Twilio recording → Whisper API → store text | backend/transcriptions/tasks.py | On call completion, transcription task runs. Text stored in Transcription model. Status=completed. | Unit (mock Whisper) | T-040 | Backend Dev |
| T-042 | S-36 | Implement Transcription viewset: list, retrieve, PATCH (edit text + track editor) | backend/transcriptions/views.py | Staff can view and edit transcription. last_edited_by updated. | Integration | T-040 | Backend Dev |
| T-043 | S-37 | Build React Transcription detail page (view text, inline edit, save button) | frontend/src/pages/TranscriptionDetailPage.tsx | Staff views transcription text. Edits inline. Saves successfully. | E2E | T-042 | Frontend Dev |
| T-044 | S-38 | Write tests: task idempotency, escalation flow (mock Twilio), TwiML output validation, transcription pipeline | backend/calling/tests/, transcriptions/tests/ | All tests pass. Idempotent task re-execution produces no duplicates. | Unit + Integration | T-035, T-041 | Backend Dev |

### Sprint 4 Task Breakdown (Weeks 7–8)

| Task ID | Story | Description | Files / Components | Acceptance Criteria | Test | Depends On | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| T-045 | S-39 | Create ReminderLog model (appointment FK, channel, delivery_status, retry_count) | backend/reminders/models.py | Migration runs. ReminderLog stores SMS/email delivery status. | Unit | T-024 | Backend Dev |
| T-046 | S-40 | Implement send_booking_reminder Celery task (SMS via Twilio + email via send_mail on booking) | backend/reminders/tasks.py | On booking, SMS and email sent. ReminderLog created with status. | Unit (mock) | T-045, T-033 | Backend Dev |
| T-047 | S-41 | Implement Celery Beat check_upcoming_reminders (hourly, 24hr window) + send_24h_reminder | backend/reminders/tasks.py | Appointments within 24hr get reminder. Already-reminded appointments skipped. | Integration | T-046 | Backend Dev |
| T-048 | S-42 | Implement reminder retry: on failure, retry once after 15 min. Log permanently failed. | backend/reminders/tasks.py | Failed reminder retried once. If still fails: status=failed, retry_count=1. | Unit | T-046 | Backend Dev |
| T-049 | S-43 | Implement GET /analytics/dashboard/ with ORM aggregates (utilization, call success, no-shows, per-doctor) | backend/analytics/views.py | Dashboard returns correct metrics. Filters by date range and doctor work. | Integration | T-024, T-034 | Backend Dev |
| T-050 | S-44 | Implement GET /analytics/export/csv/ with StreamingHttpResponse | backend/analytics/views.py | CSV download matches dashboard data for same filters. | Integration | T-049 | Backend Dev |
| T-051 | S-45 | Build React Analytics Dashboard (metric cards, filters: date range + doctor, Export CSV button) | frontend/src/pages/AnalyticsDashboardPage.tsx | Admin sees metrics. Filters update values. CSV downloads on click. | E2E | T-049 | Frontend Dev |
| T-052 | S-46 | Implement all edge cases: EC-01 (empty optional), EC-02 (past date), EC-05 (invalid phone), EC-06 (STT fail), EC-07 (deactivate doctor), EC-12 (block booked slot) | Multiple apps | Each edge case returns expected error/behavior per PRISM-R spec. | Unit + Integration | All prior | Backend Dev |
| T-053 | S-47 | Implement AuditLog middleware, verify TLS config, validate JWT expiry, run RBAC matrix test for all 26 endpoints x 4 roles | backend/users/middleware.py, tests/ | Audit log entries created. All 26 endpoints return correct 200/403 per role. | Integration | All prior | Backend Dev |
| T-054 | S-48 | Load test: 20 concurrent users on calendar, 500 slots, concurrent booking stress test, 100 call simulations | tests/load/ | Calendar loads <2s. No data corruption under concurrent booking. 100 calls queued successfully. | Load | All prior | Eng Lead |
| T-055 | S-49 | E2E tests: staff booking journey, doctor slot release, admin analytics + CSV export | tests/e2e/ | All 3 E2E tests pass on Docker Compose stack. | E2E | All prior | Frontend Dev |
| T-056 | S-50 | Seed full demo data (10 doctors, 200 patients, 7 days slots, sample call logs + transcriptions). Prepare demo script. | backend/config/management/commands/ | Demo environment ready. Walkthrough script documented. | Manual | All prior | Eng Lead |

## 7. Acceptance Criteria Mapping

Every PRISM-R acceptance criterion maps to at least one task:

| PRISM-R AC | Description | Task(s) | Sprint |
| --- | --- | --- | --- |
| FR-PM-01 | Create patient record | T-011 | Sprint 1 |
| FR-PM-04 | Duplicate phone warning | T-011 | Sprint 1 |
| FR-DS-01/02 | Doctor releases slots | T-020, T-023 | Sprint 2 |
| FR-DS-04 | Overlapping slot prevention | T-021 | Sprint 2 |
| FR-CM-04 | Concurrent double-booking prevention | T-024, T-030 | Sprint 2 |
| FR-AC-05 | Booking during AI call | T-036 | Sprint 3 |
| FR-AC-06 | Three-attempt escalation | T-035, T-037 | Sprint 3 |
| FR-CD-01/02 | Call transcription + auto-tagging | T-041 | Sprint 3 |
| FR-RM-03 | 24-hour reminder | T-047 | Sprint 4 |
| FR-AN-03 | CSV export | T-050 | Sprint 4 |
| FR-UA-06 | RBAC enforcement | T-008, T-053 | Sprint 1 + 4 |
| EC-01–12 | All edge cases | T-052 | Sprint 4 |

## 8. Dependency & Risk Analysis

Critical Path:

T-001 → T-002 → T-003/T-004 (parallel) → T-005 → T-006 → T-007/T-008 → T-011/T-015 (parallel) → T-019 → T-020 → T-024 → T-025 → T-033 → T-035 → T-041 → T-049

The critical path runs through infrastructure → auth → models → slot management → booking → calling → transcription → analytics.

Parallel Work Opportunities:

Sprint 1: Frontend (T-009, T-010, T-013, T-016) runs in parallel with Backend (T-006–T-008, T-011, T-015) after T-004 completes.

Sprint 2: Frontend calendar (T-026–T-028) runs in parallel with Backend slot logic (T-019–T-025) once API contracts are agreed.

Sprint 3: Transcription tasks (T-040–T-043) can start as soon as CallLog model (T-034) exists, parallel with call escalation (T-035–T-038).

Execution Risks:

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Twilio account setup delays Sprint 3 | Medium | High | Set up Twilio account in Sprint 1. Test with sandbox number. |
| FullCalendar integration more complex than estimated | Medium | Medium | Spike in Sprint 2 Week 3 Day 1. Fallback: simpler react-big-calendar. |
| Django Channels WebSocket flaky in Docker | Low | Medium | Redis channel layer (not in-memory). Test early in Sprint 2. |
| Whisper API latency impacts demo | Low | Low | Transcription is async. Demo shows "in progress" state then refresh. |
| Sprint 4 scope overload (reminders + analytics + hardening + demo) | High | High | Prioritize: analytics + hardening first. Reminders second. Demo prep last 2 days. |

## 9. Definition of Done (DoD)

Every task must meet ALL of the following criteria before being marked complete:

Code implemented and committed to feature branch.

All relevant tests passing (unit, integration, or E2E as specified in task).

Code reviewed via pull request (at least 1 reviewer).

Django migrations generated and committed (if model changed).

API documentation updated (DRF auto-generates via drf-spectacular).

CI pipeline green (lint + tests + Docker build).

No new security warnings (bandit for Python, ESLint security plugin for React).

## 10. Milestone Checkpoints

| Checkpoint | Date (Week) | Review | Gate Criteria |
| --- | --- | --- | --- |
| CP-1: Infrastructure Ready | End of Week 1 | Eng Lead | Docker Compose runs all 5 services. JWT login works. RBAC enforced. |
| CP-2: Data Management Ready | End of Week 2 | Eng Lead + PO | Patient CRUD and Doctor CRUD working (API + UI). Django admin configured. |
| CP-3: Scheduling Ready | End of Week 3 | Eng Lead | Slot generation, overlap detection, booking with concurrent safety, WebSocket live updates. |
| CP-4: PROTOTYPE DEMO | End of Week 4 | All Stakeholders | Full demo of scheduling workflow with seed data. Calendar real-time. Booking end-to-end. |
| CP-5: Calling Pipeline Ready | End of Week 6 | Eng Lead + PO | Twilio calls working. 3-attempt escalation. Transcription pipeline producing text. |
| CP-6: Analytics Ready | Mid Week 8 | Eng Lead | Dashboard metrics accurate. CSV export working. All edge cases handled. |
| CP-7: FINAL DEMO | End of Week 8 | All Stakeholders | Full system demo. Load test passed. Security audit complete. Documentation done. |

## 11. Execution Notes

Backend and Frontend developers should agree on API contracts (endpoint paths, request/response shapes) at the start of each sprint before parallel work begins.

Use drf-spectacular to auto-generate OpenAPI schema. Frontend can generate TypeScript types from this schema.

Twilio account should be created in Sprint 1 (even though calling is Sprint 3) to avoid account verification delays.

All Celery tasks must be designed as idempotent — re-executing a task should produce no duplicate side effects.

Django Debug Toolbar should be enabled in development to catch N+1 queries early.

Feature flags via environment variables (ENABLE_AI_CALLING, ENABLE_REMINDERS) allow Sprint 2 prototype demo without calling/reminder code active.

Sprint 4 is the densest sprint. If time is tight, prioritize: analytics dashboard > edge cases > reminders > load test > E2E tests.

## 12. Approval

Execution Plan Approval:

Approver(s): ____________________________________

Date: ____________________________________

Decision: Approved / Changes Required

## 13. AI Gold Prompt Mapping (Mandatory)

This section defines the approved AI prompt structure for generating or refining the task breakdown.

### 13.1 Approved AI Tool(s)

Primary: ChatGPT (task decomposition and planning)

Secondary (repo-aware slicing / validation): Claude Code or Gemini Code Assist

### 13.2 Gold Prompt – PRISM-M

ROLE:

You are an Engineering Manager and Tech Lead at SmartX Technologies.

OBJECTIVE:

Convert the approved PRISM-S Design Document into a detailed, testable task breakdown.

CONTEXT:

Company: SmartX Technologies

Project: MediSched AI — Django DRF + React.js + PostgreSQL + Celery + Redis

Timeline: 8 weeks (4 sprints x 2 weeks). Prototype at Week 4. 2–3 developers.

DoD: Code implemented, tests passing, PR reviewed, CI green.

INPUTS:

PRISM-S Design Document: 9 Django apps, 26 API endpoints, 8 data entities, 4-sprint rollout

PRISM-R Acceptance Criteria: 11 Gherkin scenarios, 12 edge cases, 17 NFRs

Repo structure: mono-repo /backend + /frontend, Docker Compose 5 services

INSTRUCTIONS:

Break work into epics, stories, and tasks

Ensure each task is independently buildable and testable

Map tasks to acceptance criteria

Identify dependencies and risks

Avoid oversized or vague tasks

OUTPUT FORMAT:

1. Epic list

2. Story list per epic

3. Detailed task table with acceptance criteria and tests

4. Dependency and risk notes

QUALITY CHECK:

Can tasks be assigned independently?

Does every acceptance criterion map to at least one task?

Are tasks small enough to complete and review safely?

### 13.3 Evidence for PRISM Gate (M4 → M5)

Completed Task Breakdown Structure

Tasks mapped to acceptance criteria

Clear ownership and dependencies

Execution plan approved